# PROJECT SCOPE STATEMENT

# Customer Acceptance Survey for XYZ Company's New Product

# 1. Project Scope Checklist

| No | Component | Status |
| --- | --- | --- |
| 1 | Project Objective | ✓ |
| 2 | Deliverables | ✓ |
| 3 | Milestones | ✓ |
| 4 | Technical Requirements | ✓ |
| 5 | Limits and Exclusions | ✓ |
| 6 | Acceptance Criteria | ✓ |

# 2. Project Objective

To conduct a comprehensive customer acceptance survey for XYZ Company's new food/drink product at strategic locations around Kuala Lumpur, gathering consumer feedback on product acceptance and preference compared to similar products in the market, from 1 June 2026 to 28 September 2026.

SMART Objectives:

Specific: Conduct customer acceptance survey using questionnaire instrument at selected major shopping malls in Kuala Lumpur

Measurable: Collect minimum 500 valid survey responses across 5 locations

Achievable: Utilize existing research methodology and trained survey team

Realistic: Leverage established relationships with shopping mall management

Time-bounded: 1 June - 28 September 2026

# 3. Deliverables

| No | Deliverable | Target Date |
| --- | --- | --- |
| 1 | Project Scope Statement | 19 June 2026 |
| 2 | Survey Questionnaire (Final Version) | 21 July 2026 |
| 3 | Survey Location Permissions Secured | 15 July 2026 |
| 4 | Survey Team Training Materials | 29 July 2026 |
| 5 | Completed Survey Data (500+ responses) | 17 August 2026 |
| 6 | Data Analysis Report | 2 September 2026 |
| 7 | Final Research Report | 16 September 2026 |
| 8 | Management Presentation Slides | 24 September 2026 |
| 9 | Final Project Report with Documentation | 28 September 2026 |

# 4. Milestones

| No | Milestone | Target Date |
| --- | --- | --- |
| M1 | Project Kickoff | 8 June 2026 |
| M2 | Planning Complete | 19 June 2026 |
| M3 | Questionnaire Completed | 21 July 2026 |
| M4 | Locations Secured | 15 July 2026 |
| M5 | Team Ready | 29 July 2026 |
| M6 | Survey Completed | 17 August 2026 |
| M7 | Analysis Completed | 2 September 2026 |
| M8 | Report Submitted | 16 September 2026 |
| M9 | Project Closure | 28 September 2026 |

# 5. Technical Requirements

Survey Instrument: Questionnaire designed using both open-ended and closed-ended questions

Data Collection: Minimum 100 responses per location (5 locations x 100 = 500 minimum)

Survey Locations:

- Jaya Jusco (1 Utama)

- AEON Mall Shah Alam

- Bangsar Shopping Center

- Pavilion Kuala Lumpur

- Suria KLCC

Data Analysis: Statistical analysis using SPSS or Excel

Report Format: Professional report following academic standards with proper citations

Presentation: PowerPoint presentation for management briefing

# 6. Limits and Exclusions

## Limits:

Survey scope limited to Kuala Lumpur and surrounding areas only

Maximum budget of RM 15,000 for the entire project

Survey duration from 1 June - 28 September 2026

Only consumer acceptance feedback will be collected (not product testing)

Limited to 5 major shopping mall locations

## Exclusions:

Product modification or reformulation is NOT included

Production cost analysis is NOT included

Distribution channel analysis is NOT included

Long-term market trend analysis is NOT included

Competitor product testing is NOT included

Online survey component is NOT included (face-to-face only)

# 7. Acceptance Criteria

Minimum 500 valid and completed survey questionnaires collected

Survey conducted at all 5 designated shopping mall locations

Response rate of at least 70% from approached respondents

Data analysis completed with statistical significance

Final report approved by project supervisor/management

All documentation properly archived and submitted

Management presentation delivered and approved

# 8. Stakeholders

| Stakeholder | Role |
| --- | --- |
| Project Manager | Overall project coordination and management |
| XYZ Company Management | Project sponsor and decision maker |
| Survey Coordinator | Survey operations coordination |
| Survey Team Members (3) | Data collection personnel |
| Shopping Mall Management | Location access permission |
| Survey Respondents | Target population for feedback |
| Data Analyst | Statistical analysis of collected data |
| Report Writer | Documentation and reporting |

# 9. Project Organization

Project Manager
├── Survey Coordinator
│   ├── Survey Team Member 1
│   ├── Survey Team Member 2
│   └── Survey Team Member 3
├── Data Analyst
└── Report Writer

Prepared by: [Your Name]

Date: 1 June 2026

Approved by: [Supervisor Name]

Approval Date: _______________