# WORK BREAKDOWN STRUCTURE (WBS)

# Customer Acceptance Survey for XYZ Company's New Product

# WBS Hierarchy

## (0) Project: Customer Acceptance Survey

**Main Deliverable:** Complete survey report with data analysis and management presentation

## 1.0 PROJECT INITIATION

**Summary Task**

| WBS | Task | Duration | Deliverable |
| --- | --- | --- | --- |
| 1.1 | Identify project objectives | 2 days | Objectives document |
| 1.2 | Identify stakeholders | 1 day | Stakeholder register |
| 1.3 | Develop project charter | 3 days | Project charter |
| 1.4 | **Milestone M1: Project Kickoff** | 0 days | Approval to proceed |

## 2.0 PROJECT PLANNING

**Summary Task**

| WBS | Task | Duration | Deliverable |
| --- | --- | --- | --- |
| 2.1 | Develop project scope statement | 3 days | Scope statement |
| 2.2 | Create Work Breakdown Structure | 2 days | WBS document |
| 2.3 | Develop project schedule | 2 days | Gantt chart |
| 2.4 | Plan budget and resources | 2 days | Budget plan |
| 2.5 | **Milestone M2: Planning Complete** | 0 days | Approved plans |

## 3.0 SURVEY DESIGN

**Summary Task**

| WBS | Task | Duration | Deliverable |
| --- | --- | --- | --- |
| 3.1 | Review literature on product acceptance | 5 days | Literature review |
| 3.2 | Identify research questions | 3 days | Research questions |
| 3.3 | Design questionnaire structure | 4 days | Draft questionnaire |
| 3.4 | Develop survey questions | 5 days | Questionnaire draft |
| 3.5 | Validate questionnaire (pilot test) | 3 days | Validated questionnaire |
| 3.6 | Finalize survey instrument | 2 days | Final questionnaire |
| 3.7 | **Milestone M3: Questionnaire Completed** | 0 days | Final questionnaire |

## 4.0 LOCATION PREPARATION

**Summary Task**

| WBS | Task | Duration | Deliverable |
| --- | --- | --- | --- |
| 4.1 | Identify survey locations | 2 days | Location list |
| 4.2 | Contact mall management | 3 days | Contact records |
| 4.3 | Prepare permission letters | 2 days | Permission letters |
| 4.4 | Submit permission requests | 4 days | Submission receipts |
| 4.5 | Obtain location approvals | 7 days | Approved permissions |
| 4.6 | **Milestone M4: Locations Secured** | 0 days | All approvals obtained |

## 5.0 SURVEY TEAM PREPARATION

**Summary Task**

| WBS | Task | Duration | Deliverable |
| --- | --- | --- | --- |
| 5.1 | Recruit survey team members | 4 days | Team roster |
| 5.2 | Develop training materials | 2 days | Training manual |
| 5.3 | Conduct team training | 2 days | Trained team |
| 5.4 | Prepare survey equipment | 2 days | Equipment checklist |
| 5.5 | **Milestone M5: Team Ready** | 0 days | Trained and equipped team |

## 6.0 FIELD SURVEY EXECUTION

**Summary Task**

| WBS | Task | Duration | Deliverable |
| --- | --- | --- | --- |
| 6.1 | Conduct survey at Jaya Jusco (1 Utama) | 10 days | 100+ responses |
| 6.2 | Conduct survey at AEON Mall Shah Alam | 10 days | 100+ responses |
| 6.3 | Conduct survey at Bangsar Shopping Center | 10 days | 100+ responses |
| 6.4 | Conduct survey at Pavilion KL | 10 days | 100+ responses |
| 6.5 | Conduct survey at Suria KLCC | 10 days | 100+ responses |
| 6.6 | Quality check on collected data | 2 days | Validated data |
| 6.7 | Compile survey data | 1 day | Compiled dataset |
| 6.8 | **Milestone M6: Survey Completed** | 0 days | 500+ valid responses |

## 7.0 DATA ANALYSIS

**Summary Task**

| WBS | Task | Duration | Deliverable |
| --- | --- | --- | --- |
| 7.1 | Clean and prepare data | 2 days | Clean dataset |
| 7.2 | Perform descriptive statistics | 2 days | Statistical summary |
| 7.3 | Conduct cross-tabulation analysis | 3 days | Cross-tab results |
| 7.4 | Analyze customer acceptance levels | 3 days | Acceptance analysis |
| 7.5 | Compare results across locations | 2 days | Location comparison |
| 7.6 | **Milestone M7: Analysis Completed** | 0 days | Analysis report |

## 8.0 REPORT WRITING

**Summary Task**

| WBS | Task | Duration | Deliverable |
| --- | --- | --- | --- |
| 8.1 | Write introduction and background | 2 days | Chapter 1 draft |
| 8.2 | Write methodology section | 2 days | Chapter 2 draft |
| 8.3 | Write findings and analysis | 2 days | Chapter 3 draft |
| 8.4 | Write conclusions and recommendations | 1 day | Chapter 4 draft |
| 8.5 | Compile final report | 2 days | Complete report |
| 8.6 | Review and edit report | 1 day | Final report |
| 8.7 | **Milestone M8: Report Submitted** | 0 days | Approved report |

## 9.0 PRESENTATION AND CLOSURE

**Summary Task**

| WBS | Task | Duration | Deliverable |
| --- | --- | --- | --- |
| 9.1 | Design presentation slides | 2 days | Presentation draft |
| 9.2 | Prepare presentation notes | 1 day | Speaker notes |
| 9.3 | Practice presentation | 2 days | Rehearsed presentation |
| 9.4 | Deliver management presentation | 1 day | Presentation delivery |
| 9.5 | Archive project documents | 1 day | Archived files |
| 9.6 | Conduct lessons learned review | 1 day | Lessons learned |
| 9.7 | **Milestone M9: Project Closure** | 0 days | Project closed |

# WBS Diagram

(0) Customer Acceptance Survey
│
├── 1.0 Project Initiation
│   ├── 1.1 Identify project objectives
│   ├── 1.2 Identify stakeholders
│   ├── 1.3 Develop project charter
│   └── 1.4 Milestone M1
│
├── 2.0 Project Planning
│   ├── 2.1 Develop scope statement
│   ├── 2.2 Create WBS
│   ├── 2.3 Develop schedule
│   ├── 2.4 Plan budget
│   └── 2.5 Milestone M2
│
├── 3.0 Survey Design
│   ├── 3.1 Literature review
│   ├── 3.2 Identify research questions
│   ├── 3.3 Design questionnaire structure
│   ├── 3.4 Develop survey questions
│   ├── 3.5 Validate questionnaire
│   ├── 3.6 Finalize instrument
│   └── 3.7 Milestone M3
│
├── 4.0 Location Preparation
│   ├── 4.1 Identify locations
│   ├── 4.2 Contact mall management
│   ├── 4.3 Prepare permission letters
│   ├── 4.4 Submit requests
│   ├── 4.5 Obtain approvals
│   └── 4.6 Milestone M4
│
├── 5.0 Team Preparation
│   ├── 5.1 Recruit team
│   ├── 5.2 Develop training materials
│   ├── 5.3 Conduct training
│   ├── 5.4 Prepare equipment
│   └── 5.5 Milestone M5
│
├── 6.0 Field Survey Execution
│   ├── 6.1 Jaya Jusco survey
│   ├── 6.2 AEON Mall survey
│   ├── 6.3 Bangsar survey
│   ├── 6.4 Pavilion survey
│   ├── 6.5 KLCC survey
│   ├── 6.6 Quality check
│   ├── 6.7 Compile data
│   └── 6.8 Milestone M6
│
├── 7.0 Data Analysis
│   ├── 7.1 Clean data
│   ├── 7.2 Descriptive statistics
│   ├── 7.3 Cross-tabulation
│   ├── 7.4 Acceptance analysis
│   ├── 7.5 Location comparison
│   └── 7.6 Milestone M7
│
├── 8.0 Report Writing
│   ├── 8.1 Introduction
│   ├── 8.2 Methodology
│   ├── 8.3 Findings
│   ├── 8.4 Conclusions
│   ├── 8.5 Compile report
│   ├── 8.6 Review
│   └── 8.7 Milestone M8
│
└── 9.0 Presentation and Closure
    ├── 9.1 Design slides
    ├── 9.2 Prepare notes
    ├── 9.3 Practice
    ├── 9.4 Deliver presentation
    ├── 9.5 Archive documents
    ├── 9.6 Lessons learned
    └── 9.7 Milestone M9

Work Packages Summary:

Total Major Deliverables: 9

Total Sub-deliverables: 47

Total Milestones: 9

Project Duration: 1 June - 28 September 2026