# YOUTUBE PRESENTATION SCRIPT

# Customer Acceptance Survey for XYZ Company's New Product

Duration: 10 minutes

# SLIDE 1: Title Slide (0:00 - 0:30)

Script:

"Assalamualaikum and good day. My name is [Your Name] with student ID [Your Student ID]. Today, I will be presenting my project for LMRR 1522 Perancangan Projek dan ProjectLibre course.

The title of my project is 'Customer Acceptance Survey for XYZ Company's New Food/Drink Product'. This project involves planning and executing a comprehensive market research survey to understand consumer acceptance for XYZ Company's new product."

# SLIDE 2: Project Background (0:30 - 1:30)

Script:

"Let me start with the project background. XYZ Company has successfully developed a new food/drink product that is currently in the testing phase and will be launched soon.

Before launching the product, the company needs to understand consumer acceptance and preference for this new product compared to similar products currently available in the market.

This is where our project comes in. We need to conduct a customer acceptance survey at strategic locations in Kuala Lumpur to gather valuable consumer feedback."

# SLIDE 3: Project Objectives (1:30 - 2:30)

Script:

"The main objectives of this project are:

First, to conduct a customer acceptance survey for XYZ Company's new product.

Second, to collect feedback from consumers at 5 strategic shopping mall locations in Kuala Lumpur.

Third, to analyze consumer preferences and acceptance levels.

And finally, to provide recommendations to XYZ Company's management based on our findings.

These objectives follow the SMART approach - they are Specific, Measurable, Achievable, Realistic, and Time-bounded."

# SLIDE 4: Project Scope Statement (2:30 - 3:30)

Script:

"According to the PMBOK Guide, a project scope statement should include several key components. Let me explain how we developed our scope statement.

We used the Scope Checklist method which includes:

Project Objective - clearly defined what we want to achieve

Deliverables - the specific outputs we need to produce

Milestones - key completion points in the project

Technical Requirements - the resources and capabilities needed

Limits and Exclusions - what is included and what is not

Acceptance Criteria - the conditions for project success

For our project, the main deliverables include the questionnaire, survey data from 500+ respondents, data analysis report, and the final project report."

# SLIDE 5: Work Breakdown Structure (3:30 - 4:30)

Script:

"The Work Breakdown Structure or WBS is created using the decomposition method. This means we break down the project into smaller, more manageable components.

Our WBS has 9 main phases:

Project Initiation

Project Planning

Survey Design

Location Preparation

Team Preparation

Field Survey Execution

Data Analysis

Report Writing

Presentation and Closure

Each phase is further broken down into sub-deliverables and work packages. In total, we have 55 work packages that represent the individual tasks needed to complete the project."

# SLIDE 6: Gantt Chart Overview (4:30 - 5:30)

Script:

"Now let me show you the project schedule using ProjectLibre.

The project spans from 1 June 2026 to 28 September 2026.

Looking at the Gantt chart, we can see:

Summary Tasks representing the 9 major phases

Individual activities within each phase

Milestones marked as diamonds representing key completion points

Logical relationships showing how tasks depend on each other

The project uses Finish-to-Start relationships, meaning a task must be completed before the next one can begin."

# SLIDE 7: Project Timeline (5:30 - 6:30)

Script:

"Let me walk you through the project timeline:

Phase 1 - Project Initiation: 1 June to 8 June (6 days)

Phase 2 - Project Planning: 9 June to 19 June (9 days)

Phase 3 - Survey Design: 22 June to 21 July (22 days, parallel with Phase 4)

Phase 4 - Location Preparation: 22 June to 15 July (18 days, parallel with Phase 3)

Phase 5 - Team Preparation: 16 July to 29 July (10 days)

Phase 6 - Field Survey Execution: 30 July to 17 August (13 days)

Phase 7 - Data Analysis: 18 August to 2 September (12 days)

Phase 8 - Report Writing: 3 September to 16 September (10 days)

Phase 9 - Presentation and Closure: 17 September to 28 September (8 days)

As you can see, some phases run in parallel, which helps optimize the project duration."

# SLIDE 8: Milestones (6:30 - 7:30)

Script:

"The project has 9 key milestones:

M1 - Project Kickoff (8 June)

M2 - Planning Complete (19 June)

M3 - Questionnaire Completed (21 July)

M4 - Locations Secured (15 July)

M5 - Team Ready (29 July)

M6 - Survey Completed (17 August)

M7 - Analysis Completed (2 September)

M8 - Report Submitted (16 September)

M9 - Project Closure (28 September)

These milestones serve as important control points to track project progress and ensure we stay on schedule."

# SLIDE 9: Resource Allocation (7:30 - 8:30)

Script:

"The project requires several resources:

Human Resources:

Project Manager - overall coordination

Survey Coordinator - survey operations

3 Survey Team Members - data collection

Data Analyst - statistical analysis

Report Writer - documentation

Materials:

Questionnaire forms (500+ copies)

Pens for respondents

Clipboards for field work

The resources are allocated based on the project phases, with more resources needed during the field survey execution phase."

# SLIDE 10: Quality and Risk Management (8:30 - 9:15)

Script:

"Quality management is important for this project. We have defined:

Quality Assurance - methods and processes to produce good outcomes

Quality Control - monitoring performance and results

For risk management, we identified potential risks such as:

Low response rates at certain locations

Weather conditions affecting field work

Delays in obtaining mall permissions

For each risk, we developed response strategies including mitigation, avoidance, transfer, or acceptance."

# SLIDE 11: Project Closure (9:15 - 9:45)

Script:

"The project will be closed through:

Final documentation and archiving

Lessons learned review

Management presentation delivery

Project closure approval

This ensures all project deliverables are completed and the project is formally closed."

# SLIDE 12: Conclusion (9:45 - 10:00)

Script:

"In conclusion, this project demonstrates the application of project management principles from the PMBOK Guide. We have developed a comprehensive project plan including scope statement, WBS, and Gantt chart using ProjectLibre.

The project is designed to help XYZ Company understand consumer acceptance for their new product through systematic market research.

Thank you for watching. If you have any questions, please feel free to ask."

# RECORDING NOTES

## Visual Requirements:

Slides: Create PowerPoint slides with the following content:

- Title slide with project name and student information

- Project background and objectives

- Scope statement components

- WBS diagram

- Gantt chart from ProjectLibre

- Timeline visualization

- Milestones list

- Resource allocation

- Quality and risk management

- Project closure process

- Conclusion

ProjectLibre Screenshots: Capture screenshots of:

- Gantt chart view

- Network diagram view

- WBS view

- Resource view

Screen Recording: Consider using screen recording to show:

- Navigation through the ProjectLibre file

- Different views and features

## Recording Tips:

Speak clearly and at a moderate pace

Use a quiet environment for recording

Maintain eye contact with the camera

Use a professional tone

Keep within the 10-minute time limit

Practice the presentation before recording

## Video Upload:

Upload to YouTube as unlisted or public

Add appropriate title: "LMRR 1522 - Customer Acceptance Survey Project"

Add description with student name and ID

Copy the video link for the report

# TIME BREAKDOWN

| Section | Duration | Start Time | End Time |
| --- | --- | --- | --- |
| Title Slide | 30 sec | 0:00 | 0:30 |
| Project Background | 60 sec | 0:30 | 1:30 |
| Project Objectives | 60 sec | 1:30 | 2:30 |
| Scope Statement | 60 sec | 2:30 | 3:30 |
| WBS | 60 sec | 3:30 | 4:30 |
| Gantt Chart Overview | 60 sec | 4:30 | 5:30 |
| Project Timeline | 60 sec | 5:30 | 6:30 |
| Milestones | 60 sec | 6:30 | 7:30 |
| Resource Allocation | 60 sec | 7:30 | 8:30 |
| Quality & Risk | 45 sec | 8:30 | 9:15 |
| Project Closure | 30 sec | 9:15 | 9:45 |
| Conclusion | 15 sec | 9:45 | 10:00 |
| **Total** | **10 min** | **0:00** | **10:00** |

Script prepared by: [Your Name]

Date: 28 September 2026

Course: LMRR 1522 Perancangan Projek dan ProjectLibre